## Defect Reporting
Name | Husein
Task | Final Project and Creation of Portfolio
Test Suite Name | E-Commerce Swag Labs
Defect ID | Defect Title | User Story | Defect Description | Priority | Severity | Pre-Condition/Setup | Replication Step | Expected Result | Actual Result
D-1/CSD-1 | Unable to login as locked_out_user | CSD-6 As a buyer, I want to be able to log in to the website | Unable to login using locked_out_user | 2 | 3 | The following user has been registered to the system: - User: locked_out_user - Password: secret_sauce | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button | 1. User is logged in succesfully 2. Homepage is loaded successfully | User is getting an error message that the user is locked out. Need further investigation whether it's as expected or valid defect.
D-2/CSD-1 | Logging in using performance_glitch_user is very slow to load the page | CSD-6 As a buyer, I want to be able to log in to the website | Logging in using performance_glitch_user is very slow to load the homepage | 3 | 3 | The following user has been registered to the system: - User: locked_out_user - Password: secret_sauce | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button | 1. User is logged in succesfully 2. Homepage is loaded successfully | User is logged in successfully, but homepage is ery slow to load
D-3/CSD-2 | Error in product picture | CSD-7 As a buyer, I want to be able to open the homepage and see the list of offered products | All Product picture does not match | 2 | 3 | User has logged in to homepage with Username: problem_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button | 1. User is logged in successfully 2. The homepage displays a list of products with picture that match with the title | User is logged in successfully, but homepage showcasing a list of products with wrong picture of product
D-4/CSD-2 | Error in product picture | CSD-7 As a buyer, I want to be able to open the homepage and see the list of offered products | Picture on the first product does not match the item title even when the user tries to sort | 3 | 3 | User has logged in to homepage with Username: visual_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: visual_user - Password: secret_sauce 3. Click Login button | 1. User is logged in successfully 2. The homepage displays a list of products with picture that match with the title | User is logged in successfully, but picture on the first product does not match the item title even when the user tries to sort
D-5/CSD-2 | UI placement is less attractive | CSD-7 As a buyer, I want to be able to open the homepage and see the list of offered products | UI placement is less attractive | 2 | 4 | User has logged in to homepage with Username: visual_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: visual_user - Password: secret_sauce 3. Click Login button | 1. User is logged in successfully 2. The homepage displays a list of products with picture that match with the title | User is logged in successfully, but UI placement is less attractive
D-6/CSD | Product cannot be sorted | CSD-7 As a buyer, I want to be able to open the homepage and see the list of offered products | Product cannot be sorted | 2 | 2 | User has logged in to homepage with Username: problem_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Click on dropdown sort menu 5. Choose sort price (low to high) | Products will be sorted from cheapest to most expensive | Sort cannot be clicked
D-6/CSD | Product cannot be sorted | CSD-7 As a buyer, I want to be able to open the homepage and see the list of offered products | Product cannot be sorted | 2 | 2 | User has logged in to homepage with Username: error_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Click on dropdown sort menu 5. Choose sort price (low to high) | Products will be sorted from cheapest to most expensive | Cannot be sorted, showing message "Sorting is broken! This error has been reported to Backtrace."
D-7/CSD-3 | Details product error | CSD-8 As a buyer, I want to be able to see the details of the product | Product details do not display images, titles and descriptions | 1 | 3 | User has logged in to homepage with Username: problem_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Click on item "Sauce Labs Fleece Jacket" | Showing the product details and full size image of the selected product | There are errors in the title, description and image on "Sauce Labs Fleece Jacket"
D-8/CSD-3 | Details product error | CSD-8 As a buyer, I want to be able to see the details of the product | Product details do not descriptions | 2 | 3 | User has logged in to homepage with Username: error_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: error_user - Password: secret_sauce 3. Click Login button 4. Click on item | Showing the product details and full size image of the selected product | There are errors in description
D-9/CSD-4 | "Add to cart" button cannot be clicked | CSD-9 As a buyer I want to be able to add a product to may shopping cart | "Add to cart" button cannot be clicked | 1 | 2 | User has logged in to homepage with Username: problem_user, error_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user, error_user - Password: secret_sauce 3. Click Login button 4. Click on "Add to cart" button | Item will be added to the cart and the button changes to Remove | "Add to cart" button cannot click or if "Add to cart" button can click "Remove" button cannot be click
D-10/CSD-4 | Item stuck on cart | CSD-9 As a buyer I want to be able to add a product to may shopping cart | Item stuck on cart, and cart page will be error | 1 | 1 | User has logged in to homepage with Username: problem_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Click on "Add to cart" button on Sauce Labs Fleece Jacket" 5. Click cart symbol | Showing the cart page | Blank page
D-11/CSD-4 | Cannot edit quantity field | CSD-10 As a buyer I want to be able to manage the products on my shopping car | Cannot edit quantity field | 1 | 2 | 1. User has logged in to homepage with Username: standar_user, problem_user, performance_glitch_user, error_user, visual_user Password: sauce_secret 2. Added product on cart | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Open cart page 5. Fill in quantity with number "12" | Quantity filled in "12" | Quantity cannot be clicked
D-12/CSD-5 | Checkout by filling special character on Name | CSD-11 As a buyer, I want to be able to perform checkout | Checkout by filling special character on Name | 2 | 2 | 1. User has logged in to homepage with Username: standar_user, performance_glitch_user, visual_user Password: sauce_secret 2. Added product on cart | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Open cart page 5. Click "Checkout" button 6. Fill in First Name and Last Name with Symbol (First Name: Bilal @#! Last Name: El Rumi#$) | Showing Error message and cannot click "Continue" button | There is no error message and Continued success and Showing overview page for details product checkout
D-13/CSD-5 | Checkout by filling alphabet in the postal code | CSD-11 As a buyer, I want to be able to perform checkout | Checkout by filling alphabet in the postal code | 2 | 2 | 1. User has logged in to homepage with Username: standar_user, performance_glitch_user, visual_user Password: sauce_secret 2. Added product on cart | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Open cart page 5. Click "Checkout" button 6. Fill in postal code with alphabet | Showing Error message and cannot click "Continue" button | There is no error message and Continued success and Showing overview page for details product checkout
D-14/CSD-5 | System error when filling in information on checkout on username problem_users | CSD-11 As a buyer, I want to be able to perform checkout | System error when filling in information on checkout on username problem_users | 2 | 2 | 1. User has logged in to homepage with Username: problem_user Password: sauce_secret 2. Added product on cart | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Open cart page 5. Click "Checkout" button 6. Fill in the information in the field provided (First Name: Bilal Last Name: El Rumi Postal Code: 123321) | Information is filled normally | When filling in "Last Name" field, it is instead input to "First Name" field
D-15/CSD-5 | System error when filling in information on checkout on username error_user | CSD-11 As a buyer, I want to be able to perform checkout | System error when filling in information on checkout on username error_user | 2 | 2 | 1. User has logged in to homepage with Username: problem_user Password: sauce_secret 2. Added product on cart | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Open cart page 5. Click "Checkout" button 6. Fill in the information in the field provided (First Name: Bilal Last Name: El Rumi Postal Code: 123321) | Information is filled normally | "Last Name" field cannot be filled in but there is no error and can click the "Continue" button
D-16/CSD-5 | Checkout without product | CSD-11 As a buyer, I want to be able to perform checkout | Checkout without product | 4 | 4 | 1. User has logged in to homepage with Username: standar_user, performance_glitch_user, visual_user Password: sauce_secret | 1. Open the following URL: - https://www.saucedemo.com/ 2. Login with the following user: - User: problem_user - Password: secret_sauce 3. Click Login button 4. Open cart page 5. Click "Checkout" button 6. Clcik "Continue" button | There is error message when click "Checkout" button | Checkout success and continue to infromation page
Priority
1 | - The bug affects critical functionalities or core features of the system. - Significant impact on multiple users or business operations. - Requires immediate attention and resolution to avoid major disruptions.
2 | - The bug affects important functionalities or features that are frequently used. - Impact on a significant number of users or business processes. - Requires prompt attention and resolution to prevent major inconvenience.
3 | - The bug affects non-critical functionalities or features with moderate usage. - Impact on a limited number of users or business operations. - Can be addressed within a reasonable timeframe without immediate urgency.
4 | - The bug affects minor functionalities or features with low usage. - Minimal impact on users or business processes. - Can be addressed as part of routine maintenance or in a future release.
Severity
1 | - The bug causes system crash, hang, or corruption. - Data loss or data integrity issues occur. - Security vulnerabilities that allow unauthorized access or data breaches. - Severe performance degradation impacting the majority of users.
2 | - The bug causes major functionality issues that significantly impact user experience. - A workaround may be available, but it is not feasible for regular use. - The functionality affected is important but not essential to the system's primary purpose.
3 | - Minor functionality or feature is broken. - Performance issues affecting only a few users. - Workaround is available, but it affects user experience. - Cosmetic issues that do not significantly impact usability.
4 | - Minor cosmetic issues or UI glitches. - Non-critical features are not working as expected. - Issues with low impact on user experience or system functionality.